## CDM File Cover Page
H&S Cover Sheet Information
Site | Wellington Way Shopping Centre
Site Forman
Site Forman Mobile
Date | 2024-01-08
Client | Questmap
Address | Drivers Wharf Business Park
Southampton
SO14 0PF
By | Leigh Seymour
Managing Director | Leigh Seymour
Managing Director Mobile | 07867303134
Location of nearest Hospital | Queen Alexandra Hospital
Southwick Hill Road
Portsmouth
PO6 3LY
Hospital Telephone | 02392 286000 (dial 999 in an emergency)
Police Station | Hampshire & Isle of Wight Constabulary
Waterlooville South
Swiss Road, Waterlooville
PO7 7FX
Tele | dial 999 in an emergency dial 101 if non urgent
Fire Brigade | Waterlooville Fire Station: 19
Forest End
Waterlooville, PO7 7PS
Telephone Number | 023 80644000 (Headquarters)
Dial 999 in an emergency

## Contents Page
Site | Wellington Way Shopping Centre
Index
1 Company Policy/Statement
2 Construction phase health and safety plan
3 Project directory
4 Site Rules
5 Site Emergency plan
6 Drawings
7 Programme of works
8 Site Method Statements & Risk Assessments Tick list
9 Method Statements
10 Risk Assessments
11 COSSHH Assessments
12 Certificate of Employers liability
13 Site Visitors log
14 Accident Report form
15 Site Induction Log
16 Weekly site audit checklist
17 Daily Diary
18 Blank method statements and risk assessments
19 F10 Notification
20 Hoarding Licence
21 Permit to Work
22 Variation site instruction
23 Goods received sheet
24 Completion notice certificate
25 Equipment and workplace inspection
26 Plant Off Hired
Recived by: | ....................................................................
Print name: | .....................................................................
On Behalf of: | .....................................................................
Date: | .....................................................................

## Policy statement
Health & Safety Policy
Our primary concern is for the safety of our employees, contractors, clients and the general public. It is our policy to ensure we safeguard the health and welfare of all our employees at work and to provide an environment that is safe and with out risk to health.
We will endeavour to create the safest working environment that is practicable as we understand that without the confidence of our employees and clients we would have no business.
We are commited at all levels of our business to ensure that continous improvements are made to reduce the risk of accidents by constantly auditing our practices to ensure that every project is carried out to the highest standards.
Quality Statement
Highfield Construction has a commitment to continual quality and standards improvement for our products and services and is a trusted and proven supplier to the retail sector.
Customer satisfaction is of critical importance to our continued success, our processes, products and on site procedures are regularly audited to continuously monitor and improve in order to exceed these high standards that are already in place. We understand the demands of the retailers needs and take great pride in being a strong link in producing a quality product, delivered on time, and at the right cost.
Environmental Policy
We understand that the type of work we do and the materials we use has an impact upon the environment and society that we share. We aim to minimise the impact by continued development and research into new materials and methods of working. Our commitment extends to minimising the amount of waste and only using approved Environment Agency approved contractors, and where possible we will use suppliers that extend to replenishing resources for future generations.

## Construction Phase
Construction Phase Health & Saftey Plan
Client
Site | Wellington Way Shopping Centre
1 | Project Directory
2 | Description of Works
3 | General Statement
4 | Site Location Description
5 | Project Management Structure
6 | Health and Safety Standards
7 | Information for Contractors
8 | Communication and Co-operation
9 | Activities with Risks to Health and Safety
10 | Emergency Procedures
11 | Welfare
12 | Information for People on Site
13 | Site Rules
14 | Induction, security and on site training
15 | Health and Safety File

## CP Project Directory
Project Directory
CLIENT | Wellington Way Shopping Centre
Questmap | Contact: | Peter Harding
| Tel: | 023 8038 2800
Fax:
Email:
PRINCIPAL CONTRACTOR
Highfield Construction | Contact: | Leigh Seymour
| Tel: | 07867303134
Fax:
Mobile:
Email:
Site Manager:
Mobile:
PROJECT MANAGEMENT & QUANTITY SURVEYORS
Contact:
Tel:
Fax:
Mobile:
Email:
Site Manager:
Mobile:
CDM CO-ORDINATOR
N/A | Contact:
Tel:
Fax:
Mobile:
Email:
Site Manager:
Mobile:
DESIGNER
RS Studio | Contact:
| Tel: | 02382 542011
Fax:
Mobile:
| Email: | info@rs-studio.co.uk
Site Manager:
Mobile:
HEALTH & SAFETY EXECUTIVE
Contact:
Tel:
Fax:
Mobile:
Email:
SIGNAGE
TBC | Contact:
Tel:
Fax:
Mobile:
Email:
PLUMBING
TBC | Contact:
Tel:
Fax:
Mobile:
Email:
ELECTRICAL
TBC | Contact:
Tel:
Fax:
Mobile:
Email:
AIR CONDITIONING & DUCTING
Contact:
TBC | Tel:
Fax:
Mobile:
Email:
Tenant Liaison Manager
TBC | Contact:
Tel:
Fax:
Mobile:
Email:

## CP Description of works
Construction Phase Health & Saftey Plan
Wellington Way Shopping Centre
Description of Works
Demolition of first floor. Extension and reconfiguration to provide flats.
* | Demolition of first floor
* | Construction of timber frame walls
* | Installation of truss roof
* | Weathering of walls and roof
* | Thermal Insulation
* | New Doors and Windows
* | First Fix Electrics
* | First Fix Plumbing
* | Stairs and Access
* | Internal Plaster Board and Skim
* | Carpentry
* | Second Fix Electrics
* | Second Fix Plumbing
* | Decoration
* | Flooring
* | External Works
The project consists of the redevelopment of existing shops,
the works will be undertaken as programmed
over 547 days.
The project uses traditional construction materials.
Programme:
Works begin – March 1st 2024
Duration – 18 months Provisional
Handover date is September 1st 2025

## Cp General Statement
Construction Phase Health & Saftey Plan
3 General Statements
Highfield Construction will ensure that Contractors and all persons at work on site, so far as is reasonably practicable, comply with the provisions of the Health and Safety Plan and the specified rules contained within.
All contractors / suppliers selected are suitable to provide the services required, based on quality, cost and health and safety competence.
Sub contractors are appointed after examining their safety approach / performances. Historic activities are considered and a sound safety approach to work methods, consideration of others and evidence of Health and safety training requirements. Contract terms must include, where necessary, the provision of COSHH and other necessary assessments by sub contractors prior to awarding the contract.
Suppliers of materials, in accordance with the requirements under the COSHH regulations, must submit data and hazard sheets for distribution to ensure safe use of those materials.

## CP Site Location Descriptions
Construction Phase Health & Saftey Plan
4 Site/Location Descriptions
Wellington Way Shopping Centre
Waterlooville
PO7 7EB
All deliveries to be booked in Via Leigh Seymour

## CP 5 management structure
Construction Phase Health & Saftey Plan
| Project Manager: | Leigh Seymour
| Site Foreman: | Leigh Seymour
| First Aider: | Leigh Seymour
Roles and Responsibilities
Project Manager | Leigh Seymour
Operations Manager: | Leigh Seymour
Mobile Number: | 07867303134
Be satisfied with the competence of all persons and companies to undertake works on the project.
To provide adequate resource to ensure the project can be delivered safely within programme.
To ensure that the Construction Phase H & S Plan is sufficiently developed to allow the commencement of works by the CDM Coodinator.
To put in place a site safety strategy including adequate Site Rules, Fire Plans, PPE, Permits to Work and other items as required.
Site Manager
Site Agent/Foreman: | Leigh Seymour
Mobile Number: | 7867303134
To co-ordinate, monitor and ensure that all works are carried out in a safe manner.
To ensure that method statements and risk assessments are in place and adequate for all operations.
To enforce the Site Rules in place and ensure that all persons before entering site undergo the Site Specific Induction.
To liaise with the Project Manager and other applicable parties on programme,
safety and all other issues to maintain communication throughout the works.
Operatives
To fully co-operate and comply with all Rules/Procedures/Legislation to ensure a safe controlled work environment

## CP6 H&S
Construction Phase Health & Saftey Plan
6 Health & Safety Standards
To complete the building works to the required programme without causing any accidents, incidents or near misses to operatives, members of the public or any other persons.
To ensure the completed building works functions in an efficient and safe manner, can be maintained safety and eventually deconstructed or demolished without undue risk.
To ensure that due consideration is given to the health and safety issues related to the design prior to arranging to carry out the work.
Highfield Construction will notify the Employer of any changes to this Health and Safety Plan and shall notify (if appointed) the CDM Coordinator of any changes, which may affect the designer’s considerations and/or require co-ordination of the designer’s further considerations including the completion of all elements of design work by specialist sub-contractors or the appointed design team.
Highfield Construction will ensure that proper planning of the construction work takes place and that suitable management procedures are in place to safely control the works, with particular reference to the phasing of work and continued use of the retail area.
To ensure that the completed health and safety file provides relevant information.
To assess the health and safety implications of any Architects Instructions and advise the Contract Administrator, prior to execution, of any significant risks.
The CDM coordinator is to be informed of any unforeseen eventuality that occurs during the project execution that may result in substantial design changes, and which may affect the Health and Safety Plan.
All current legislation applies.

## CP 7,8,9
Construction Phase Health & Saftey Plan
7 Information for Contractors
All operatives must sign in and out of the site morning and evening in accordance with site rules. A site induction will be carried out for all operatives working within the work area. This will outline means of escape, location of the first aid station, first aiders, etc. Permits to work, Site-specific rules and procedures.
8 Communications and Co-operation
Highfield Construction is fully committed to the Practical Management of Health and Safety on site. All contractors will be expected to participate pro-actively on all issues such as the production of and adherence to Risk Assessments, Method Statements etc. The Project Manager / Site Manager will carry out site audits randomly during the works.
All persons on site, or their representatives, will be given the opportunity to give their views on health and safety.
Where necessary, arrangements will be made to have monthly meetings between contractors to ensure co-ordination of views, particularly where high risk activities are being undertaken. Consultation will also take place with the project CDM Co-ordinator or lead designer for the project, where it is necessary to alter or change designs.
9 Activities with risks to Health and Safety
All activities with risks to health and safety identified by Highfield Construction will require a risk assessment and a method statement developing to show how they will be effectively managed to reduce the risk. Contractors will be unable to commence works if relevant risk assessments and method statements have not been produced.
The risk assessments and method statements may be specific to a particular trade or cover site-wide issues.
All risk assessments and method statements should be clearly communicated to those who are to undertake the works and also those who may be affected by the works.

## CP 10 emegency procedure
Construction Phase Health & Saftey Plan
10 Emergency Procedures
Queen Alexandra Hospital | Always Dial 999 in an emergency
Southwick Hill Road
Portsmouth
PO6 3LY
02392 286000 (dial 999 in an emergency)
Please see the enclosed map on a separate page.
Fire
A works plan is enclosed with this file and fire exits and routes are to be marked on to this plan on site.
A Site Fire Plan will be displayed within the site clearly showing the emergency exit routes and assembly point in the event of a fire. Leigh Seymour will be given responsibility to act as the Fire Warden on site and ensuring fire safety is maintained. This will be communicated to all persons entering site at Induction stage and the persons’ name will be displayed on the Site Fire Plan.
Accidents/First Aid
All accidents should be recorded on an Accident Report Form.
The name of the First Aider is: Leigh Seymour
In the event of an incident requiring hospital treatment
The nearest hospital is:

## CP 11,12,13
Construction Phase Health & Saftey Plan
11 Welfare
Toilet Facilities
Existing toilet facilities to be used .
Washing Facilities
Existing on site washing facilities established.
Water is provided on site
Rest Facilities
site manager will designate an area on a daily basis
12 Information for people on site
All staff and Visitors entering the premises will be required to sign in and out.
All staff and visitors are to make their prescence known to the site Foreman before proceeding through the site.
A copy of Highfield Contruction's Employers Liability Insurance Certificate will be displayed.
Other signage will be displayed as required and in accordance with The Health and Safety (Safety, Signs and Signals) Regulations 1996.
13 Site Rules
The Site Rules in force will be brought to the attention of those who will be affected by them prior to entering site. All persons will be expected to follow the Site Rules.
Should the Site Rules not be followed it may result in eviction from site.

## CP 14 , 15
Construction Phase Health & Saftey Plan
14 Site induction, Security and on site training
Induction to site is a legal requirement under the health and safety at work act 1974 and also under supporting legislation.
A site induction will be carried out by a member of the site management team. Every operative who receives an induction to site must sign the site induction log to verify that he/she has understood the instructions, will agree to abide by the conditions stated and has seen and understood their own (where applicable) risk assessments and/or method statements.
Emergency procedures for site are an integral part of the induction process and all persons will be made aware of alarms, exit routes and assembly points to allow safe evacuation from site.
Short term visitors must be aware of the site rules; hence an abridged induction procedure will be undertaken that will include emergency procedures. Where short tem visitors are not inducted they must be escorted at all times. Records of inductions can be found in the induction log within this health and safety file and available for inspection on site at any time, upon completion of the project it will be archived with the health and safety file for future reference if required.
Prior to commencement of any work, all operatives will participate in a formal site induction training course, which will include details of all site rules and the procedures for operatives passing information regarding health and safety matters.
15 Health & Safety File
All method statements, risk assessments etc from sub-contractors working for Highfield Construction are included within this document, as per the requirements of the pretender health and safety plan.

## Project Directory
Project Directory
CLIENT | The Fragrance Shop
Questmap | Contact: | Peter Harding
| Tel: | 023 8038 2800
Fax:
Email:
PRINCIPAL CONTRACTOR
Highfield Construction | Contact: | Leigh Seymour
| Tel: | 07867303134
Fax:
Mobile:
Email:
Site Manager:
Mobile:
PROJECT MANAGEMENT
Contact:
Tel:
Fax:
Mobile:
Email:
Site Manager:
Mobile:
CDM CO-ORDINATOR
Contact:
Tel:
Fax:
Mobile:
Email:
Site Manager:
Mobile:
DESIGNER
RS Studio | Contact:
| Tel: | 02382 542011
Fax:
Mobile:
| Email: | info@rs-studio.co.uk
Site Manager:
Mobile:
Architect
RS Studio | Contact:
| Tel: | 02382 542011
Fax:
Mobile:
| Email: | info@rs-studio.co.uk
SIGNAGE & FLOORING
TBC | Contact:
Tel:
Fax:
Mobile:
Email:
ELECTRICAL
TBC | Contact:
Tel:
Fax:
Mobile:
Email:
AIR CONDITIONING
TBC | Contact:
Tel:
Fax:
Mobile:
Email:
Acoustic consultant
| Contact: | Shaun De La Rue
Tel:
Fax:
Mobile:
Email:
Structural engineer
Hamill Davies | Contact: | Brian Hamill
Ivydaledale Lower Chase Road | Tel: | 01489 893596
Southampton | Fax:
SO32 2PB | Mobile:
Email:
Building Control
MC Plan and Site Services | Contact:
Unit J3 | Tel: | 01202 744966
The Fulcrum | Fax:
Vanatge Way, Poole | Mobile:
BH12 4NU | Email:

## Rules
SITE RULES
1 | All Personnel must undergo a site induction
2 | Strictly No Smoking.
3 | Always wear safety boots/or shoes, hard hats and other safety equipment as required
4 | Do not operate any plant or equipment unless you are trained and authorised
5 | Only competent persons, who are authorised to do so, may erect alter or dismantle scaffolding, false work or excavation support.
6 | Keep your working area clean, tidy and free from tripping hazards, placing any waste in the skips/bins provided.
7 | Do not work at any edge from which you could fall more than 2 metres, unless edge protection or fall arrest equipment is in place.
8 | Make sure you have sight of the COSHH assessment for any hazardous substances you may come into contact with.
9 | Report any defect or unsafe practices to your foreman/site manager.
10 | Report any accidents or near misses to the site manager and ensure they are logged
11 | Co-operate with your employer and the safety requirements of the principal contractor.
12 | Request to see the method statement and risk assessments for any activity you are required to undertake.
13 | All food and drinks must be consumed in the welfare area and not at the workplace – wrappers/containers to be disposed of accordingly.
14 | Leave the welfare facilities in a clean and tidy condition.
15 | Understand the fire and emergency procedures.
16 | Clear up and report all spillages of fuel, oil and other hazardous substances.
17 | Do not tamper with, alter or remove any plant or equipment unless you are authorised to do so.
18 | Any electrical connection to an existing supply must be made by a competent and trained operative through the site manager. All electrical equipment to be tested.
19 | All operatives will comply with the requests/instructions given/instructed by the site manager.
20 | A permit must be obtained prior to commencing any hot works.
21 | Only 110v, or lower power tools are allowed on site
22 | Keep everyone’s safety first.
23 | If in any doubt speak to the site manager.
24 | No Radios on Site
FAILURE TO COMPLY WILL LEAD TO REMOVAL FROM SITE AND YOUR EMPLOYER INFORMED

## method & risk tick list
SITE METHOD STATEMENTS &
RISK ASSESSEMENTS TICK LIST
Site | Wellington Way Shopping Centre
Company Name | Trade, Activity or hazzard | M/S & R/A required on site |  | Date Due | Date Received
|  | YES | NO
Highfield Construction | Stud walls | P |  | 2024-03-01
Highfield Construction | Waste removal | P |  | 2024-03-01
Highfield Construction | Opening Works | P |  | 2024-03-01
Highfield Construction | Joinery works | P |  | 2024-03-01
Highfield Construction | Decoration | P |  | 2024-03-01
Highfield Construction | Electrical Works | P |  | 2024-03-01

## Wall opening method
METHOD STATEMENT
Company Name: |  | Highfield Construction | Date: | 2024-01-08
Site:
Prepared By: |  | Leigh Seymour
Works to be completed: Wall openings
1 | Survey holes for bulkhead works
2 | Cut walls /Floors with masonry hand tools power drills
3 | Remove fittings from walls, keep tidy
4 | Ensure all waste is bagged
5 | Use scaffolding to access high areas
Subcontractor undertaking the work
Name |  | Role
Site Operatives |  | Joiners & Labourers
Plant or equipment used
Plant/Equipment |  | Trained Operatives
SDS Hammer drill, Masonry Saw, Cordless Drill/Driver/Sledge Hammer
Joiners & Labourers
What PPE should be worn?
PPE |  | Activity
Hard Hats |  | Cutting materials
Safety Footwear |  | Manual handling
Hi-Vis Vests
Eye Protection
Are work permits or other requirements required?
Requirement |  | Detail
Hot work permit |  | Required prior to commencement of any works that may
produce heat or sparks
Protection of the public
Activity |  | Detail
Contractors and |  | PPE to be worn at all times as per site rules
Visitors to site |  | visitors to sign in/ brief H&S induction
Site Specific Rules
Site Rule |  | Detail
Refer to Health & Safety File - Section 9 - Site Rules
Area/Other people affected
Area or people |  | Location
Systems or procedures eg Security and Alarm System
System affected |  | Detail
Copy of method statement
Name |  | Notes
Site File
Highfield Construction
Client

## Decorations Method
METHOD STATEMENT
Company Name: |  | Highfield Construction | Date: | 2024-01-08
Client: |  | Questmap
Site:
Prepared By: |  | Leigh Seymour
Works to be completed: Decorations
1 | Emulsion of walls & Ceilings
a | apply base coat to required area and allow to dry,all as manufacturers instructions
b | apply filler to any inperfections in wall, level off, and allow to harden
c | sand off excess filler, ready to receive further coat
d | Apply further coat to required area
e | repeat b,c & d until satisfactory result (usually a further 2 coats)
2 | Undercoat and Gloss of all Woodwork / Metal work
a | Sand required area with abrasive paper
b | apply base undercoat to required area and allow to dry, all as per manufactures instructions
c | lightly sand area with abrasive paper and apply gloss - allow to dry
d | repeat c until satisfactory result (usually a further 2 coats)
Subcontractor undertaking the work
Name |  | Role
Site Operatives |  | Decorators
Plant or equipment used
Plant/Equipment |  | Trained Operatives
Paint Brushes, paints, thinners and cleaners
Decorators
What PPE should be worn?
PPE |  | Activity
Hard Hats |  | Cutting materials
Safety Footwear |  | Manual handling
Dust Masks
Hi-Vis Vests
Eye Protection
Are work permits or other requirements required?
Requirement |  | Detail
Protection of the public
Activity |  | Detail
Contractors and |  | PPE to be worn at all times as per site rules
Visitors to site
Site Specific Rules
Site Rule |  | Detail
Refer to Health & Safety File - Section 9 - Site Rules
Area/Other people affected
Area or people |  | Location
Systems or procedures eg Security and Alarm System
System affected |  | Detail
Copy of method statement
Name |  | Notes
Site File
Highfield Construction
Client

## Removal of waste method
METHOD STATEMENT
Company Name: |  | Highfield Construction | Date: | 2024-01-08
Site:
Prepared By: |  | Leigh Seymour
Works to be completed: Removal of waste material
1 | All operatives undertaking the removal of waste are to report to the site manager for induction and toolbox talk.
2 | All materials will be carefully removed from the site and disposed of at a licenced tip.
3 | The storage of materials in the skip/bins will be in such a manner as to reduce any risk of injury to site personnel
4 | All waste specific to each task will be cleared from the working area upon completion
5 | The removal of equipment containing hazardous substances (CFC’s etc) will be undertaken by approved agencies in accordance with the specific Risk and Method Statement provided by the relevant contractor
6 | All fixings through redundant or removed materials, such as screws and nails etc, will have these removed or flattened prior to handling.
7 | All operatives will wear the appropriate PPE (hardhat, protective footwear, high vis vests, gloves. Dust masks if required
8 | All waste will be removed from the site when any storage facility is full.
9 | Exit routes are to be maintained at all times.
10 | Any loose or lightweight debris within the skip/bins will be covered or tied down to avoid wind disturbance
11 | Under no circumstances are any hazardous waste liquids to be poured away through gulleys or drains. Any waste liquids are to be contained and removed from site by an approved contractor or as described in the relevant contractors specific Risk and Method Statement.
12 | Any hazardous waste that cannot be removed from site at the end of a shift is to be placed in a secure locked container within the shop store area. Shop staff are to be informed at handover
Subcontractor undertaking the work
Name |  | Role
Site Operatives |  | Joiners & Labourers
Plant or equipment used
Plant/Equipment |  | Trained Operatives
Skips etc |  | Joiners & Labourers
What PPE should be worn?
PPE |  | Activity
Hard Hats |  | Removal of waste materials
Safety Footwear
Gloves
Hi-Vis Vests
Eye Protection
Are work permits or other requirements required?
Requirement |  | Detail
Protection of the public
Activity |  | Detail
Contractors and |  | PPE to be worn at all times as per site rules
Visitors to site
Site Specific Rules
Site Rule |  | Detail
Refer to Health & Safety File - Section 9 - Site Rules
Area/Other people affected
Area or people |  | Location
Systems or procedures eg Security and Alarm System
System affected |  | Detail
Copy of method statement
Name |  | Notes
Site File
Highfield Construction
Client

## Installation joinery method
METHOD STATEMENT
Company Name: |  | Highfield Construction | Date: | 2024-01-08
Site:
Prepared By: |  | Leigh Seymour
Works to be completed: Installation of joinery works
Set out following items as floor plan
1 | Install Doors and Frames
2 | Fix skirting & Architrive
3 | Stud partitions
4 | Kitchen Units
5 | Cills and thresholds
6
7
Subcontractor undertaking the work
Name |  | Role
Site Operatives |  | Joiners & Labourers
Plant or equipment used
Plant/Equipment |  | Trained Operatives
SDS Hammer drill, Jig Saw, Chop Saws, Router, Cordless Drill/Driver
Joiners & Labourers
What PPE should be worn?
PPE |  | Activity
Hard Hats |  | Working at height
Safety Footwear |  | Cutting materials
Hi-Vis Vests |  | Manual handling
Eye Protection
Are work permits or other requirements required?
Requirement |  | Detail
Hot work permit |  | Required prior to commencement of any works that may
produce heat or sparks
Protection of the public
Activity |  | Detail
Contractors and |  | PPE to be worn at all times as per site rules
Visitors to site
Site Specific Rules
Site Rule |  | Detail
Refer to Health & Safety File - Section 9 - Site Rules
Area/Other people affected
Area or people |  | Location
Systems or procedures eg Security and Alarm System
System affected |  | Detail
Copy of method statement
Name |  | Notes
Site File
Highfield Construction
Client

## Installation stud method
METHOD STATEMENT
Company Name: |  | Highfield Construction | Date: | 2024-01-08
Site: |  | Wellington Way Shopping Centre
Prepared By: |  | Leigh Seymour
Works to be completed: Installation of stud walling
1 | Set out walls as floor plan
2 | Fix sole plate as setting out
3 | Plumb and fix studs & fix top rail
4 | Cut wall panels using saw with dust extraction
5 | Lift cut boards to correct position, fix one elevation only to allow access for M&E etc. Scaffolding to be used to access high level fixings.
6 | Fix doors and frame as schedule through metal partition to back of frame - no visible fixings.
7 | Fit 2nd elevation panels (where necessary) once all M&E, electrical works connected
8 | Cut and fix cover trims to wall panel joints as required
9 | Tape and fill any plasterboard joints ready for decoration
10 | All waste materials to be placed in skip/bins provided
Subcontractor undertaking the work
Name |  | Role
Site Operatives |  | Joiners & Labourers
Plant or equipment used
Plant/Equipment |  | Trained Operatives
SDS Hammer drill, Jig Saw, Chop Saws, Router, Cordless Drill/Driver
Joiners & Labourers
What PPE should be worn?
PPE |  | Activity
Hard Hats |  | Working at height
Safety Footwear |  | Cutting materials
Hi-Vis Vests |  | Manual handling
Eye Protection
Are work permits or other requirements required?
Requirement |  | Detail
Hot work permit |  | Required prior to commencement of any works that may
produce heat or sparks
Protection of the public
Activity |  | Detail
Contractors and |  | PPE to be worn at all times as per site rules
Visitors to site
Site Specific Rules
Site Rule |  | Detail
Refer to Health & Safety File - Section 9 - Site Rules
Area/Other people affected
Area or people |  | Location
Systems or procedures eg Security and Alarm System
System affected |  | Detail
Copy of method statement
Name |  | Notes
Site File
Highfield Construction
Client

## Strip out method
METHOD STATEMENT
Company Name: |  | Highfield Construction | Date: | 2024-01-08
Site:
Prepared By: |  | Leigh Seymour
Works to be completed: Strip out works
Works to be completed in accordance with scope of works
1 | Dismantle walls (partitions and Blockwork) as floor plan.
2 | Dismantle ceilings - remove ceiling tiles, internal track sections and wall tracks
3 | Removal of floor coverings
4 | Works area to be kept clean and tidy
5 | Ensuring all waste material are placed in skips/bins provided
Subcontractor undertaking the work
Name |  | Role
Site Operatives |  | Joiners & Labourers
Plant or equipment used
Plant/Equipment |  | Trained Operatives
SDS Hammer drill, Jig Saw, Chop Saws, Cordless Drill/Driver/Sledge Hammer
Joiners & Labourers
What PPE should be worn?
PPE |  | Activity
Hard Hats |  | Working at height
Safety Footwear |  | Cutting materials
Hi-Vis Vests |  | Manual handling
Eye Protection
Are work permits or other requirements required?
Requirement |  | Detail
Hot work permit |  | Required prior to commencement of any works that may
produce heat or sparks
Protection of the public
Activity |  | Detail
Contractors and |  | PPE to be worn at all times as per site rules
Visitors to site
Site Specific Rules
Site Rule |  | Detail
Refer to Health & Safety File - Section 9 - Site Rules
Area/Other people affected
Area or people |  | Location
Systems or procedures eg Security and Alarm System
System affected |  | Detail
Copy of method statement
Name |  | Notes
Site File
Highfield Construction
Client

## Tiling method
METHOD STATEMENT
Company Name: |  | Highfield Construction | Date: | 2024-01-08
Site:
Prepared By: |  | Leigh Seymour
Works to be completed: Tiling works
Works to be completed in accordance with scope of works & Tiling drawings
1 | Set out starting point of tiles as per drawing information provided and where possible cordon off the working area from other trades
2 | apply adhesive to area in Meter squared sections ensuring levels are adhered too
3 | Lay tiles (as point1) with spacers 2-3mm, gently tapping to ensure tiles are bedded to adhesive
4 | Any cut tiles should be cut with the appropriate equipment provided and the relevant PPE and laid as point 3
5 | Allow adhesive time to dry, remove spacers from joint lines
6 | Grout joint lines with specified grout and rub in
7 | Clean down tiles with the relevant specified cleaner
8 | Ensure all waste material are placed in skips/bins provided
Subcontractor undertaking the work
Name |  | Role
Site Operatives |  | Tilers & Labourers
Plant or equipment used
Plant/Equipment |  | Trained Operatives
Tile Cutters, Tile Saws, angle grinder
Tilers & Labourers
What PPE should be worn?
PPE |  | Activity
Hard Hats |  | Working at height
Safety Footwear |  | Cutting materials
Hi-Vis Vests |  | Manual handling
Eye Protection
Are work permits or other requirements required?
Requirement |  | Detail
Hot work permit |  | Required prior to commencement of any works that may
produce heat or sparks
Protection of the public
Activity |  | Detail
Contractors and |  | PPE to be worn at all times as per site rules
Visitors to site
Site Specific Rules
Site Rule |  | Detail
Refer to Health & Safety File - Section 9 - Site Rules
Area/Other people affected
Area or people |  | Location
other trades |  | cordon off area where ever possible
Systems or procedures eg Security and Alarm System
System affected |  | Detail
Copy of method statement
Name |  | Notes
Site File
Highfield Construction
Client

## Fire Risks
RISK ASSESSMENT
Site Location:- | [5 empty] | Date | 2024-01-08
Operation
Fire Risks
Hazard
Discarded Cigarette Ends
Poorly Maintained Electrical Equipment and Faulty Sockets/Wiring
Areas Allowed to Gather Dust Debris and Combustable Material
Lack of Staff Training
Faulty Fire Fighting Equipment
No Fire Plan Action
SEVERITY POTENTIAL
3 | MAJOR |  | 2 |  | SERIOUS | 1 | SLIGHT
LIKELIHOOD
3 | HIGH |  | 2 |  | MEDIUM | 1 | LOW
RISK LEVEL = SEVERITY X LIKELIHOOD
|  | 3 | M | H | H
|  | 2 | L | M | H
|  | 1 | L | L | M
|  |  | 1 | 2 | 3
Controls
Works to be undertaken as per site rules
Appropriate PPE for task to be used
No Smoking Policy in Operation Through out the Building
All Equipment Checked on a Regularly & and Any Faulty Items are Taken out of Service and Repaired
Any Faulty Electrical Sockets/Wiring are Immediately Isolated, & a Qualified Electricain is Called
The Building is Regulary Cleaned to Avoid Build up of Dust and Debris
All Combustable Material is Removed from the building
Staff Have Been Given Full Training of Their Required Action in Event of a Fire
Fire Fighting Equipment is Serviced on a Annually Basis
Fire Plan of Action Has Been Made Aware to All Staff
Monitored by: |  | All

## Hot work risk
RISK ASSESSMENT
Site Location:- | [6 empty] | Date | 2024-01-08
Operation
Hot Works
Hazard
Power Tools | [5 empty] | Electric Shock
Manual Handling | [5 empty] | Moving Machinery Parts
Hand Tools | [5 empty] | Sharp Objects
Fire
SEVERITY POTENTIAL
3 |  | MAJOR |  | 2 |  | SERIOUS | 1 | SLIGHT
LIKELIHOOD
3 |  | HIGH |  | 2 |  | MEDIUM | 1 | LOW
RISK LEVEL = SEVERITY X LIKELIHOOD
|  |  | 3 | M | H | H
|  |  | 2 | L | M | H
|  |  | 1 | L | L | M
|  |  |  | 1 | 2 | 3
Controls
1 | At least 2 suitable portable fire extinguishers will be available for immediate use
within the area of hot work operations and all person involved and undertaking fire watch
duties to be trained in their use. Any automatic fire detection systems should be isolated
only in the area where works are undertaken and only for the period of the work.
2 | Combustible materials and flammable liquids should be removed from an area within
10 metres of the hot work adjacent areas which may be in danger of ignition either
directly or from conducted heat
3 | If there are any combustible material that cannot be removed, any holes, gaps in walls,
floors or ceilings where sparks could pass through they should be covered in
incombustible material.
4 | Floors of combustible material in the designated area should be covered with sheets
of incombustible protective material or wetted and covered with sand
5 | Where work is carried out on building panels, an assessment should be made on
insulating or other materials behind or forming the core of the panels.
6 | Allow adequate ventilation
7 | Identify any gas or other services adjacent to or below the area of hot work and isolate
and protect them.
8 | All persons carrying out the hot work and undertaking the fire watch should know how to
raise the fire alarm and be aware of any emergency procedures
9 | Confirm all other contractors/operators on site are aware that hot work is being undertaken
and that there is no application of paints or flammable solvent based substances
10 | A 1 hour fire watch to be maintained after all works are completed
Monitored by: |  |  | ALL

## Materials Risk
RISK ASSESSMENT
Site | [6 empty] | 2024-01-08
Operation
Material cutting & finishing/fixing
Hazard
Power Tools
Slips, Trips and Falls
Manual Handling
Hand Tools
Fire
SEVERITY POTENTIAL
3 | MAJOR |  | 2 |  | SERIOUS | 1 | SLIGHT
LIKELIHOOD
3 | HIGH |  | 2 |  | MEDIUM | 1 | LOW
RISK LEVEL = SEVERITY X LIKELIHOOD
|  | 3 | M | H | H
|  | 2 | L | M | H
|  | 1 | L | L | M
|  |  | 1 | 2 | 3
Controls
Works to be undertaken as per site rules
Appropriate PPE for task to be used
All tools to be Pat Tested
Equipment to be visually checked each day
Good housekeeping - clear walkways
Cutting of materials which could give off sparks or generate extreme temperatures should not take place unless hot works permit has been issued.
Designated areas to be set up for recurring operations such as use of chop saws and routers and the cutting of sheet materials
Monitored by: |  |  | ALL

## Working height Risk
RISK ASSESSMENT
Site Location:- | [5 empty] | Date | 2024-01-08
Operation
Working at height
Hazard
Falling objects
Falling people
SEVERITY POTENTIAL
3 | MAJOR |  | 2 |  | SERIOUS | 1 | SLIGHT
LIKELIHOOD
3 | HIGH |  | 2 |  | MEDIUM | 1 | LOW
RISK LEVEL = SEVERITY X LIKELIHOOD
|  | 3 | M | H | H
|  | 2 | L | M | H
|  | 1 | L | L | M
|  |  | 1 | 2 | 3
Controls
Works to be undertaken as per site rules
Appropriate PPE for task to be used
Ladders to be tied & footed
Working platform to be clear & tidy and appropriate to task
Ensure barriers are present
Monitored by: |  | ALL

## Power tools risk
RISK ASSESSMENT
Site Location:- | [5 empty] | Date | 2024-01-08
Operation
Portable Power Tools
Hazard
Electric Shock
Moving Machinery Parts
Sharp Objects
SEVERITY POTENTIAL
3 | MAJOR |  | 2 |  | SERIOUS | 1 | SLIGHT
LIKELIHOOD
3 | HIGH |  | 2 |  | MEDIUM | 1 | LOW
RISK LEVEL = SEVERITY X LIKELIHOOD
|  | 3 | M | H | H
|  | 2 | L | M | H
|  | 1 | L | L | M
|  |  | 1 | 2 | 3
Controls
Works to be undertaken as per site rules
Appropriate PPE for task to be used
Power tools to be used by competent person
Equipment to be visually checked each day
Equipment to be pat tested
Monitored by: |  | ALL

## Vistors Log
SITE VISITORS LOG
Site Location |  | #REF!
#REF!
DATE | NAME |  | COMPANY | TIME IN | TIME OUT | REASON FOR VISIT | SIGNATURE

## Accident form
ACCIDENT REPORT FORM
Date
Time
Please give location of accident:
Site
First Name |  | Surname |  |  | Age
Address
Postcode
Did the person go back to
Work |  | Hospital |  | Home
Please tick as appropriate
Please give details of accident and what caused it.
Give details of the injury and what parts of the body were injured
Details of person filling in this form
First Name |  |  | Surname
Signature |  |  | Date

## Site induction
SITE INDUCTION
FOR ALL PEOPLE WORKING ON SITE WITH NO EXCEPTIONS
Site:
I confirm that I agree to comply with the site rules and regulations and have been made aware of the health and safety file, emergency plan and fire exits
These include :
Key Personnel | Senior Management H&S Commitment |  | Accident and near miss reporting
Project Outline | Work Method Risk Assessments |  | Responsibility and horseplay
Hours of work | Hazardous Substances |  | Fire Procedure
Arriving on site | Traffic Routes |  | First Aid
Welfare facilities | High Risk and Out of Bounds areas |  | Alcohol and drugs
No Smoking | Buried Services |  | Tidiness on site (Housekeeping)
Tower Scaffolds | Abrasive Wheels |  | Security arrangements
Permits to Work | Protective Clothing/Apparatus |  | Toolbox talks (on site training)
INDUCTEE | COMPANY | DATE | SIGNATURE | INDUCTOR

## Week Audit checklist
WEEKLY SITE AUDIT CHECKLIST
Site Location:-
Date: | 2024-01-08
No | Item | Yes/No | Comments/Action
1 | Are all risk assessments available?
2 | Are there method statements for significant risks?
3 | Have all sub contractors been inducted?
4 | Are first aid facilities and appointed person available?
5 | Is the fire plan displayed and assembly point clearly indicated?
6 | Are fire extinguishers in position?
7 | Is a permit to work used for all hot works?
8 | Is the entrance free from obstruction?
9 | Are working areas clearly identified?
10 | Are rest and welfare facilities acceptable?
11 | Is PPE being worn?
12 | Is COSHH information available?
13 | Are flammable substances being stored safely away?
14 | Has electrical equipment been tested?
15 | Where electrical works are not from a 110V supply has a method statement been provided?
16 | Is scaffolding tested?
17 | Are steps and ladders in good condition?
18 | Is the height suitable to work safely?
19 | Are ladders being used on firm level surfaces?
20 | Are ladders tied and footed?

## Hot works Permit
PERMIT TO WORK
Applicable to all operations involving flame, sparks, hot air or arc welding and cutting equipment, brazing and soldering equipment, blow lamps and other equipment producing heat or naked flames or other high risk activities
Details of Operation
Location of work:
Details of work:
Start Date: |  | Completion Date:
General Precautions
Hot Works should only be undertaken where a safer method of working is not available
Wherever possible items to be subjected to hot works should be removed to a safe area designated for that purpose
A trained person, not directly involved with the work, should provide a continuous fire watch during and for at least 1 hour following the hot work completion to ensure that the working area and all adjacent areas are free of smouldering materials.
Checklist Before Hot Work Commences |  |  |  | Tick once check is complete
1 | At least 2 suitable portable fire extinguishers should be available for immediate use
within the area of hot work operations and all person involved and undertaking fire watch
duties to be trained in their use. Any automatic fire detection systems should be isolated
only in the area where works are undertaken and only for the period of the work.
2 | Combustible materials and flammable liquids should be removed from an area within
10 metres of the hot work adjacent areas which may be in danger of ignition either
directly or from conducted heat
3 | If there are any combustible material that cannot be removed, any holes, gaps in walls,
floors or ceilings where sparks could pass through they should be covered in
incombustible material.
4 | Floors of combustible material in the designated area should be covered with sheets
of incombustible protective material or wetted and covered with sand
5 | Where work is carried out on building panels, an assessment should be made on
insulating or other materials behind or forming the core of the panels.
6 | Allow adequate ventilation
7 | Identify any gas or other services adjacent to or below the area of hot work and isolate
and protect them.
8 | All persons carrying out the hot work and undertaking the fire watch should know how to
raise the fire alarm and be aware of any emergency procedures
9 | Confirm all other contractors/operators on site are aware that hot work is being undertaken
and that there is no application of paints or flammable solvent based substances
Authorisation to proceed
I hereby declare that the above has been made known to the person in charge of the work.
I consider the above mentioned area is safe for operations to commence.
Signed on behalf of Highfield Construction |  |  |  | Print
Date
Acceptance by competent person
I acknowledge receipt of this permit and understand the precautions/comments above.
Neither I nor the persons under my control will work on any other activity or location than those specified.
Signed |  |  | Print
Name of Company |  |  | Date
Clearance following Completion of Works
A | All hot waste materials should be removed and disposed of safely
B | All equipment, including gas cylinders, should be removed
C | Blow lamps and gas cylinders should only be fitted/changed in the open
Final Check
Maintain fire watch and regular inspections for a period of 60 minutes after completion of the hot works
as specified under General Precautions
I hereby declare that the work described above is complete and the precautions noted
above have been complied with. The area has been inspected and is free of risk and
all tools/equipment have been withdrawn
Signed |  |  | Print
Name of Company |  |  | Date
Cancellation
I hereby declare this permit cancelled. I have received the copies of the permit back and the area has
been inspected and is free of risk
Signed on behalf of Highfield Construction |  |  |  | Print
Date